## OSS Interface
Module Name: oss.py Description: Create and Delete bucket and object, List object, Create Folder, Simple Upload
|  | Click2Cloud Testing Team Status |  | Aliyun Team Status
|  | Total Test Cases | 27 | Total Test Cases | 27
|  | No. of Test Case Passed | 27 | No. of Test Case Passed | 27
|  | No. of Test Case Failed | 0 | No. of Test Case Failed | 0
|  | No. of Test Case Partially Passed | 0 | No. of Test Case Partially Passed | 0
|  | No. of Test Case have Concern | 0 | No. of Test Case have Concern | 0
[6 empty] | Click2Cloud Testing Team |  | Aliyun Testing Team
| # | Test Case Name | Playbook File | Description | Expected Result | C2C Actual Result | C2C Status | Aliyun Actual Result | Aliyun Status | Comment for Failure
Create Bucket | 1 | Verify Bucket creation with mode parameter validation | CreateBucketModeparamValidation | In this Playbook, we tried to validate mode parameter at the time of bucket creation | Scenario 1 - Bucket should not be created Scenario 2 - Bucket should not be created Scenario 3 - Bucket should not be created Scenario 4 - Bucket should not be created | Scenario 1 - Bucket is not created Scenario 2 - Bucket is not created Scenario 3 - Bucket is not created Scenario 4 - Bucket is not created | Pass | As expected | Pass
| 2 | Verify Bucket creation with permission parameter validation | CreateBucketPermissionParamValidation | In this Playbook, we tried to validate permission parameter at the time of bucket creation | Scenario 1 - Bucket should not be created Scenario 2 - Bucket should not be created Scenario 3 - Bucket should not be created Scenario 4 - Bucket should be created Scenario 4.1 - Bucket should be deleted | Scenario 1 - Bucket is not created Scenario 2 - Bucket is not created Scenario 3 - Bucket is not created Scenario 4 - Bucket is created Scenario 4.1 - Bucket is deleted | Pass | As expected | Pass
| 3 | Verify Bucket creation with region parameter validation | CreateBucketRegionParamValidation | In this Playbook, we tried to validate region parameter at the time of bucket creation | Scenario 1 - Bucket should not be created Scenario 2 - Bucket should be created Scenario 2.1 - Bucket should be deleted Scenario 3 - Bucket should not be created Scenario 4 - Bucket should be created Scenario 4.1 - Bucket should be deleted | Scenario 1 - Bucket is not created Scenario 2 - Bucket is created Scenario 2.1 - Bucket is deleted Scenario 3 - Bucket is not created Scenario 4 - Bucket is created Scenario 4.1 - Bucket is deleted | Pass | As expected | Pass
| 4 | Verify Bucket creation with all alias | CreateBucketWithAlias | In this Playbook, we tried to create a bucket with all alias | Scenario 1 - Bucket should be created Scenario 2 - Bucket should be deleted | Scenario 1 - Bucket is created Scenario 2 - Bucket is deleted | Pass | As expected | Pass
| 5 | Verify Bucket creation with all mandatory parameters | CreateBucketWithAllParameters | In this Playbook, we tried to create a bucket with all mandatory parameters | Scenario 1 - Bucket should be created Scenario 2 - Bucket should be deleted | Scenario 1 - Bucket is created Scenario 2 - Bucket is deleted | Pass | As expected | Pass
| 6 | Verify Bucket creation with all mandatory permissions | CreateBucketWithAllPermissions | In this Playbook, we tried to create a bucket with all permissions | Bucket should not be created | Bucket is not created | Pass | As expected | Pass
| 7 | Verify Bucket creation with Bucket parameter validation | CreateBucketWithBucketParamValidation | In this Playbook, we tried to validate bucket parameter at the time of bucket creation | Scenario 1 - Bucket should not be created Scenario 2 - Bucket should not be created Scenario 3 - Bucket should not be created Scenario 4 - Bucket should be created Scenario 4.1 - Bucket should be deleted Scenario 5 - Bucket should not be created Scenario 6 - Bucket should be created Scenario 6.1 - Bucket should be deleted Scenario 7 - Bucket should not be created Scenario 8 - Bucket should not be created Scenario 9 - Bucket should not be created | Scenario 1 - Bucket is not created Scenario 2 - Bucket is not created Scenario 3 - Bucket is not created Scenario 4 - Bucket is created Scenario 4.1 - Bucket is deleted Scenario 5 - Bucket is not created Scenario 6 - Bucket is created Scenario 6.1 - Bucket is deleted Scenario 7 - Bucket is not created Scenario 8 - Bucket is not created Scenario 9 - Bucket is not created | Pass | As expected | Pass
| 8 | Verify Bucket creation with duplicate Bucket name | CreateBucketWithDuplicateName | In this Playbook, we tried to create a bucket with duplicate name | Scenario 1 - Bucket should be created Scenario 2 - Bucket should not be created | Scenario 1 - Bucket is created Scenario 2 - Bucket is not created | Pass | As expected | Pass
Delete Load Blancer | 9 | Verify Bucket deletion with mode parameter validation | DeleteBucketModeParamValidation | In this Playbook, we tried to validate mode parameter at the time of bucket deletion | Scenario 1 - Bucket should not be deleted Scenario 2 - Bucket should not be deleted Scenario 3 - Bucket should not be deleted Scenario 4 - Bucket should not be deleted | Scenario 1 - Bucket is not deleted Scenario 2 - Bucket is not deleted Scenario 3 - Bucket is not deleted Scenario 4 - Bucket is not deleted | Pass | As expected | Pass
| 10 | Verify Bucket deletion which is in use | DeleteBucketWhichIsInUse | In this Playbook, we tried to delete bucket which contains data | Bucket should not be deleted | Bucket is not deleted | Pass | As expected | Pass
| 11 | Verify Bucket deletion with all alias | DeleteBucketWithAlias | In this Playbook, we tried to delete a bucket with all alias | Scenario 1 - Bucket should be created Scenario 2 - Bucket should be deleted | Scenario 1 - Bucket is created Scenario 2 - Bucket is deleted | Pass | As expected | Pass
| 12 | Verify Bucket deletion with all mandatory parameters | DeleteBucketWithAllParameters | In this Playbook, we tried to delete a bucket with all mandatory parameters | Scenario 1 - Bucket should be created Scenario 2 - Bucket should be deleted | Scenario 1 - Bucket is created Scenario 2 - Bucket is deleted | Pass | As expected | Pass
| 13 | Verify Bucket deletion with Bucket parameter validation | DeleteBucketWithBucketNameParamValidation | In this Playbook, we tried to validate bucket parameter at the time of bucket deletion | Scenario 1 - Bucket should not be deleted Scenario 2 - Bucket should not be deleted Scenario 3 - Bucket should not be deleted Scenario 4 - Bucket should not be deleted | Scenario 1 - Bucket is not deleted Scenario 2 - Bucket is not deleted Scenario 3 - Bucket is not deleted Scenario 4 - Bucket is not deleted | Pass | As expected | Pass
| 14 | Verify Bucket deletion with Bucket of different region | DeleteBucketWithRegionDiff | In this Playbook, we tried to delete a bucket with region different than bucket's region | Scenario 1 - Bucket should be created Scenario 2 - Bucket should not be created Scenario 3 - Bucket should be deleted | Scenario 1 - Bucket is created Scenario 2 - Bucket is not created Scenario 3 - Bucket is deleted | Pass | As expected | Pass
Create Folder | 15 | Verify folder creation with same folder name | CreateDuplicateFolder | In this Playbook, we tried to create a folder with duplicate folder name | Scenario 1 - Folder should not be created Scenario 2 - Folder should not be created | Scenario 1 - Folder is created Scenario 2 - Folder is not created | Pass | As expected | Pass
| 16 | Verify folder creation with Bucket parameter validation | CreateFolderBucketParamValidation | In this Playbook, we tried to validate bucket parameter at the time of folder creation | Scenario 1 - Folder should not be created Scenario 2 - Folder should not be created Scenario 3 - Folder should not be created Scenario 4 - Folder should not be created | Scenario 1 - Folder is not created Scenario 2 - Folder is not created Scenario 3 - Folder is not created Scenario 4 - Folder is not created | Pass | As expected | Pass
| 17 | Verify folder creation with mode parameter validation | CreateFolderModeParamValidation | In this Playbook, we tried to validate mode parameter at the time of folder creation | Scenario 1 - Folder should not be created Scenario 2 - Folder should not be created Scenario 3 - Folder should not be created Scenario 4 - Folder should not be created | Scenario 1 - Folder is not created Scenario 2 - Folder is not created Scenario 3 - Folder is not created Scenario 4 - Folder is not created | Pass | As expected | Pass
| 18 | Verify folder creation with all mandatory parameters | CreateFolderWithAllParameters | In this Playbook, we tried to create a folder with all mandatory parameters | Scenario 1 - Bucket should be created Scenario 2 - Folder should be created | Scenario 1 - Bucket iscreated Scenario 2 - Folder is created | Pass | As expected | Pass
| 19 | Verify folder creation with Folder Name parameter validation | CreateFolderWithFolderNameParamValidation | In this Playbook, we tried to validate folder name parameter at the time of folder creation | Scenario 1 - Folder should not be created Scenario 2 - Folder should not be created Scenario 3 - Folder should not be created Scenario 4 - Folder should not be created Scenario 5 - Folder should be created Scenario 6 - Folder should be created Scenario 7 - Folder should not be created | Scenario 1 - Folder is not created Scenario 2 - Folder is not created Scenario 3 - Folder is not created Scenario 4 - Folder is not created Scenario 5 - Folder is created Scenario 6 - Folder is created Scenario 7 - Folder is not created | Pass | As expected | Pass
Delete Object | 20 | Verify object deletion with all mandatory parameters | DeleteObjectWithMandatoryParametersonly | In this Playbook, we tried to modify internet spec of SLB with bandwidth parameter validation | Object should be deleted | Object is deleted | Pass | As expected | Pass
| 21 | Verify object deletion with all parameters | DeletingObjectWithAllTheParameters | In this Playbook, we tried to modify internet spec of SLB with Load Balancer Id parameter validation | Object should be deleted | Object is deleted | Pass | As expected | Pass
List Bucket Object | 22 | Verify object listing with all the parameters | ListBucketObjectWithAllTheParameters | In this Playbook, we tried to set Load Balancer Name with Load Balancer Id parameter validation | Objects should be listed | Objects are listed | Pass | As expected | Pass
| 23 | Verify object listing with mandatory parameters | ListBucketObjectWithMandatoryParameterOnly | In this Playbook, we tried to set Load Balancer Name with Region parameter validation | Objects should be listed | Objects are listed | Pass | As expected | Pass
Simple Upload | 24 | Verify simple upload with bucket name parameter validation | SimpleUploadWithBucketNameParameterValidation | In this Playbook, we tried to set Load Balancer Status from Active to inactive | Scenario 1 - Bucket should be created Scenario 2 - Object should not be uploaded Scenario 3 - Bucket shouldbe deleted | Scenario 1 - Bucket is created Scenario 2 - Object is not uploaded Scenario 3 - Bucket shouldbe deleted | Pass | As expected | Pass
| 25 | Verify simple upload with expiration parameter validation | SimpleUploadWithExpirationParameterValidation | In this Playbook, we tried to set Load Balancer Status with Region parameter validation | Scenario 1 - Bucket should be created Scenario 2 - Object should be uploaded Scenario 3 - Object should not be uploaded Scenario 4 - Object should be uploaded Scenario 5 - Object should not be uploaded Scenario 6 - Object should not be uploaded Scenario 7 - Object should be deleted Scenario 8 - Bucket should be deleted | Scenario 1 - Bucket iscreated Scenario 2 - Object is uploaded Scenario 3 - Object is not uploaded Scenario 4 - Object is uploaded Scenario 5 - Object is not uploaded Scenario 6 - Object is not uploaded Scenario 7 - Object is deleted Scenario 8 - Bucket is deleted | Pass | As expected | Pass
| 26 | Verify simple upload with headers parameter validation | SimpleUploadWithHeadersParameterValidation | In this Playbook, we tried to set Load Balancer Status with alias | Scenario 1 - Bucket should be created Scenario 2 - Object should be uploaded Scenario 3 - Object should be uploaded Scenario 4 - Object should be deleted Scenario 5 - Bucket should be deleted | Scenario 1 - Bucket iscreated Scenario 2 - Object is uploaded Scenario 3 - Object is uploaded Scenario 4 - Object is deleted Scenario 5 - Bucket is deleted | Pass | As expected | Pass
| 27 | Verify simple upload with mandatory parameters | SimpleUploadWithMandatoryParametersOnly | In this Playbook, we tried to set Load Balancer Status with all parameters | Scenario 1 - Bucket should be created Scenario 2 - Object should be uploaded Scenario 3 - Object should be deleted Scenario 4 - Bucket should be deleted | Scenario 1 - Bucket iscreated Scenario 2 - Object is uploaded Scenario 3 - Object is deleted Scenario 4 - Bucket is deleted | Pass | As expected | Pass

## Database
Module Name: rds.py Description: Create and Delete database
|  | Click2Cloud Testing Team Status |  | Aliyun Team Status
|  | Total Test Cases | 13 | Total Test Cases | 13
|  | No. of Test Case Passed | 13 | No. of Test Case Passed | 13
|  | No. of Test Case Failed | 0 | No. of Test Case Failed | 0
|  | No. of Test Case Partially Passed | 0 | No. of Test Case Partially Passed | 0
|  | No. of Test Case have Concern | 0 | No. of Test Case have Concern | 0
[6 empty] | Click2Cloud Testing Team |  | Aliyun Testing Team
| # | Test Case Name | Playbook File | Description | Expected Result | C2C Actual Result | C2C Status | Aliyun Actual Result | Aliyun Status | Comment for Failure
Create Database | 1 | Verify database creation with Character Set Name parameter validation | CreateDatabaseCharacterSetNameParamValidation | In this Playbook, we tried to validate Character Set Name parameter at the time of database creation | Scenario 1 - Database should not be created Scenario 2 - Database should not be created Scenario 3 - Database should not be created Scenario 4 - Database should not be created | Scenario 1 - Database is not created Scenario 2 - Database is not created Scenario 3 - Database is not created Scenario 4 - Database is not created | Pass | As Expected | Pass
| 2 | Verify database creation with Command parameter validation | CreateDatabaseCommandParamValidation | In this Playbook, we tried to validate Command parameter at the time of database creation | Scenario 1 - Database should not be created Scenario 2 - Database should not be created Scenario 3 - Database should not be created Scenario 4 - Database should not be created | Scenario 1 - Database is not created Scenario 2 - Database is not created Scenario 3 - Database is not created Scenario 4 - Database is not created | Pass | As Expected | Pass
| 3 | Verify database creation with description parameter validation | CreateDatabaseDescParamValidation | In this Playbook, we tried to validate description parameter at the time of database creation | Scenario 1 - Database should be created Scenario 1.1 - Database should be deleted Scenario 2 - Database should be created Scenario 2.1 - Database should be deleted Scenario 3 - Database should not be created | Scenario 1 - Database is created Scenario 1.1 - Database is deleted Scenario 2 - Database is created Scenario 2.1 - Database is deleted Scenario 3 - Database is not created | Pass | As Expected | Pass | Thread dependency on instance status
| 7 | Verify database creation with Instance Id parameter validation | CreateDatabaseInstanceIdParamValidation | In this Playbook, we tried to validate Instance Id parameter at the time of database creation | Scenario 1 - Database should not be created Scenario 2 - Database should not be created Scenario 3 - Database should not be created Scenario 4 - Database should not be created | Scenario 1 - Database is not created Scenario 2 - Database is not created Scenario 3 - Database is not created Scenario 4 - Database is not created | Pass | As Expected | Pass
| 8 | Verify database creation with Database Name parameter validation | CreateDatabaseNameParamValidation | In this Playbook, we tried to validate Database Name parameter at the time of database creation | Scenario 1 - Database should not be created Scenario 2 - Database should not be created Scenario 3 - Database should not be created Scenario 4- Database should not be created Scenario 5 - Database should be created Scenario 5.1 - Database should be deleted Scenario 6 - Database should be created Scenario 6.1 - Database should be deleted | Scenario 1 - Database is not created Scenario 2 - Database is not created Scenario 3 - Database is not created Scenario 4- Database is not created Scenario 5 - Database is created Scenario 5.1 - Database is deleted Scenario 6 -Database is created Scenario 6.1 -Database is deleted | Pass | As Expected | Pass | Thread dependency on instance status
| 9 | Verify database creation with Region parameter validation | CreateDatabaseRegionParamValidation | In this Playbook, we tried to validate Region parameter at the time of database creation | Scenario 1 - Database should not be created Scenario 2 - Database should not be created Scenario 3 - Database should not be created Scenario 4 - Database should not be created | Scenario 1 - Database is not created Scenario 2 - Database is not created Scenario 3 - Database is not created Scenario 4 - Database is not created | Pass | As Expected | Pass
| 10 | Verify database creation with all parameters | CreateDatabaseWithAllParameters | In this Playbook, we tried database creation with all parameters | Scenario 1 - Database should be created Scenario 2 - Database should be deleted | Scenario 1 - Database is created Scenario 2 - Database is deleted | Pass | As Expected | Pass
| 11 | Verify database creation with duplicate database name | CreateDatabaseWithDuplicateName | In this Playbook, we tried database creation with duplicate database name | Scenario 1- Database should be created Scenario 2 - Database should be created Scenario 3 - Database should be deleted | Scenario 1 - Database is created Scenario 2 - Database is not created Scenario 3 - Database is deleted | Pass | As Expected | Pass
Delete Database | 1 | Verify database deletion with command parameter validation | DeleteDatabaseCommandParamValidation | In this Playbook, we tried to delete database with command parameter validation | Scenario 1 - Database should not be deleted Scenario 2 - Database should not be deleted Scenario 3 - Database should not be deleted Scenario 4 - Database should not be deleted | Scenario 1 - Database is not deleted Scenario 2 - Database is not deleted Scenario 3 - Database is not deleted Scenario 4 - Database is not deleted | Pass | As Expected | Pass
| 2 | Verify database deletion with instance id parameter validation | DeleteDatabaseInstanceIdParamValidation | In this Playbook, we tried to delete database with instance id parameter validation | Scenario 1 - Database should not be deleted Scenario 2 - Database should not be deleted Scenario 3 - Database should not be deleted Scenario 4 - Database should not be deleted | Scenario 1 - Database is not deleted Scenario 2 - Database is not deleted Scenario 3 - Database is not deleted Scenario 4 - Database is not deleted | Pass | As Expected | Pass
| 3 | Verify database deletion with Database Name parameter validation | DeleteDatabaseNameParamValidation | In this Playbook, we tried to validate Database Name parameter at the time of database deletion | Scenario 1 - Database should not be deleted Scenario 2 - Database should not be deleted Scenario 3 - Database should not be deleted Scenario 4 - Database should not be deleted | Scenario 1 - Database is not deleted Scenario 2 - Database is not deleted Scenario 3 - Database is not deleted Scenario 4 - Database is not deleted | Pass | As Expected | Pass
| 4 | Verify database deletion with Region parameter validation | DeleteDatabaseRegionParamValidation | In this Playbook, we tried to validate Region parameter at the time of database deletion | Scenario 1 - Database should not be deleted Scenario 2 - Database should not be deleted Scenario 3 - Database should not be deleted Scenario 4 - Database should not be deleted | Scenario 1 - Database is not deleted Scenario 2 - Database is not deleted Scenario 3 - Database is not deleted Scenario 4 - Database is not deleted | Pass | As Expected | Pass
| 5 | Verify database deletion with all mandatory parameters | DeleteDatabaseWithAllParameters | In this Playbook, we tried database deletion with all mandatory parameters | Database should be deleted | Database is deleted | Pass | As Expected | Pass

## Instance
Module Name: rds.py Description: Create and Delete RDS Instance, Switching database
Restarting and Modifying RDS Instance, Changing RDS Instance Type
|  | Click2Cloud Testing Team Status |  | Aliyun Team Status
|  | Total Test Cases | 25 | Total Test Cases | 25
|  | No. of Test Case Passed | 25 | No. of Test Case Passed | 25
|  | No. of Test Case Failed | 0 | No. of Test Case Failed | 0
|  | No. of Test Case Partially Passed | 0 | No. of Test Case Partially Passed | 0
|  | No. of Test Case have Concern | 0 | No. of Test Case have Concern | 0
[6 empty] | Click2Cloud Testing Team |  | Aliyun Testing Team
| # | Test Case Name | Playbook File | Description | Expected Result | C2C Actual Result | C2C Status | Aliyun Actual Result | Aliyun Status | Comment for Failure
| 1 | Verify RDS instance creation with all the parameters | CreateRdsInstanceWithAllTheParameters | In this Playbook, we tried to create RDS instance with all the parameters | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is released | Pass | As expected | Pass
| 2 | Verify RDS instance creation with command Parameter Validation | CreateRdsInstanceWithCommandParameterValidation | In this Playbook, we tried to validate Command parameter at the time of RDS instance creation | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should not be created Scenario 3 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is not created Scenario 3 - RDS instance is released | Pass | As expected | Pass
| 3 | Verify RDS instance creation with Instance Description Parameter Validation | CreateRdsInstanceWithInstanceDescriptionParameterValidation | In this Playbook, we tried to validate Instance Description parameter at the time of RDS instance creation | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should be created Scenario 3 - RDS instance should be created Scenario 4 - RDS instance should not be created Scenario 5 -RDS instance should be created Scenario 6 - RDS instance should be created Scenario 7 - RDS instance should not be created Scenario 8 - RDS instance should be created Scenario 9 - RDS instance should not be created Scenario 10 - RDS instance should be released Scenario 11 - RDS instance should be released Scenario 12 - RDS instance should be released Scenario 13 - RDS instance should be released Scenario 14 - RDS instance should be released Scenario 15 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is created Scenario 3 - RDS instance is created Scenario 4 - RDS instance is not created Scenario 5 - RDS instance is created Scenario 6 - RDS instance is created Scenario 7 - RDS instance is not created Scenario 8 - RDS instance is created Scenario 9 - RDS instance is not created Scenario 10 - RDS instance is released Scenario 11 - RDS instance is released Scenario 12 - RDS instance is released Scenario 13 - RDS instance is released Scenario 14 - RDS instance is released Scenario 15 - RDS instance is released | Pass | As expected | Pass
| 4 | Verify RDS instance creation with Mandatory parameters | CreateRdsInstanceWithMandatoryParametersOnly | In this Playbook, we tried to create RDS instance with mandatory parameters | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is released | Pass | As expected | Pass
| 5 | Verify RDS instance creation with Region Parameter Validation | CreateRdsInstanceWithRegionParameterValidation | In this Playbook, we tried to validate region parameter at the time of RDS instance creation | Scenario 1 - RDS instance should not be created Scenario 2 - RDS instance should not be created Scenario 3 -RDS instance should be created Scenario 4 - RDS instance should be created Scenario 5 - RDS instance should be released Scenario 6 - RDS instance should be released | Scenario 1 - RDS instance is not created Scenario 2 - RDS instance is not created Scenario 3 - RDS instance is created Scenario 4 - RDS instance is created Scenario 5 - RDS instance is released Scenario 6 - RDS instance is released | Pass | As expected | Pass
| 6 | Verify RDS instance creation with Security Ip List Parameter Validation | CreateRdsInstanceWithSecurityIpListparameterValidation | In this Playbook, we tried to validate Security Ip List parameter at the time of RDS instance creation | Scenario 1 -RDS instance should be created Scenario 2 - RDS instance should not be created Scenario 3 - RDS instance should not be created Scenario 4 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is not created Scenario 3 - RDS instance is not created Scenario 4 - RDS instance is released | Pass | As expected | Pass
| 7 | Verify RDS instance creation with Wait, Waittimeout And Db Tags Parameter Validation | CreateRdsInstanceWithWaitWaittimeoutAndDbTagsParameterValidation | In this Playbook, we tried to validate Wait, Waittimeout And Db Tags parameters at the time of RDS instance creation | Scenario 1 - RDS instance should not be created Scenario 2 - RDS instance should not be created Scenario 3 -RDS instance should be created Scenario 4 - RDS instance should be released | Scenario 1 - RDS instance is not created Scenario 2 - RDS instance is not created Scenario 3 - RDS instance is created Scenario 4 - RDS instance is released | Pass | As expected | Pass
| 8 | Verify RDS instance creation with zone Parameter Validation | CreateRdsInstanceWithZoneParameterValidation | In this Playbook, we tried to validate zone parameter at the time of RDS instance creation | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should not be created Scenario 3 - RDS instance should be created Scenario 4 - RDS instance should be created Scenario 5 - RDS instance should be released Scenario 6 - RDS instance should be released Scenario 7 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is not created Scenario 3 - RDS instance is created Scenario 4 - RDS instance is created Scenario 5 - RDS instance is released Scenario 6 - RDS instance is released Scenario 7 - RDS instance is released | Pass | As expected | Pass
Modify RDS Instance | 1 | Verify RDS instance modification with command Parameter Validation | ModifyRdsInstanceWithCommandParameterValidation | In this Playbook, we tried to validate command parameter at the time of RDS instance modification | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should not be modified Scenario 3 - RDS instance should not be modified Scenario 4 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is not modified Scenario 3 - RDS instance is not modified Scenario 4 - RDS instance is released | Pass | As expected | Pass
| 2 | Verify RDS instance modification with all Parameters | ModifyRdsInstanceWithMandatoryParametersOnly | In this Playbook, we tried to modify RDS instance with all the parameters | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should be modified Scenario 3 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is modified Scenario 3 - RDS instance is released | Pass | As expected | Pass | API Error
Release RDS Instance | 1 | Verify releasing of RDS instance with all scenarios | ReleaseRdsInstanceWithAllScenarios | In this Playbook, we tried to release RDS instance with all the scenarios | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should not be released Scenario 3 - RDS instance should not be released Scenario 4 - RDS instance should not be released Scenario 5 - RDS instance should not be released Scenario 6 - RDS instance should not be released Scenario 7 - RDS instance should not be released Scenario 8 - RDS instance should be released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is not released Scenario 3 - RDS instance is not released Scenario 4 - RDS instance is not released Scenario 5 - RDS instance is not released Scenario 6 - RDS instance is not released Scenario 7 - RDS instance is not released Scenario 8 - RDS instance is released | Pass | As expected | Pass
Restarting RDS Instance | 1 | Verify restarting of RDS instance with all scenarios | RestartingRdsInstanceWithAllScenarios | In this Playbook, we tried to restart RDS instance with all the scenarios | Scenario 1 - RDS instance should be created Scenario 2 - RDS instance should not restart Scenario 3 - RDS instance should not restart Scenario 4 - RDS instance should not restart Scenario 5 - RDS instance should not restart Scenario 6 - RDS instance should not restart Scenario 7 - RDS instance should released | Scenario 1 - RDS instance is created Scenario 2 - RDS instance is not restarted Scenario 3 - RDS instance is not restarted Scenario 4 - RDS instance is not restarted Scenario 5 - RDS instance is not restarted Scenario 6 - RDS instance is not restarted Scenario 7 - RDS instance is released | Pass | As expected | Pass
Switching Database | 1 | Verify switching of primary and standby database with Command parameter validation | SwitchingDbCommandParamValidation | In this Playbook, we tried to validate Command parameter at the time of switching primary and standby database | Scenario 1 - Primary and standby database should not be switched Scenario 2 - Primary and standby database should not be switched Scenario 3 - Primary and standby database should not be switched Scenario 4 - Primary and standby database should not be switched | Scenario 1 - Primary and standby database are not switched Scenario 2 - Primary and standby database are not switched Scenario 3 - Primary and standby database are not switched Scenario 4 - Primary and standby database are not switched | Pass | As expected | Pass
| 2 | Verify switching of primary and standby database with instance id parameter validation | SwitchingDbInstanceIdParamValidation | In this Playbook, we tried to validate instance id parameter at the time of switching primary and standby database | Scenario 1 - Primary and standby database should not be switched Scenario 2 - Primary and standby database should not be switched Scenario 3 - Primary and standby database should not be switched Scenario 4 - Primary and standby database should not be switched | Scenario 1 - Primary and standby database are not switched Scenario 2 - Primary and standby database are not switched Scenario 3 - Primary and standby database are not switched Scenario 4 - Primary and standby database are not switched | Pass | As expected | Pass
| 3 | Verify switching of primary and standby database with node id parameter validation | SwitchingDbNodeIdParamValidation | In this Playbook, we tried to validate node id parameter at the time of switching primary and standby database | Scenario 1 - Primary and standby database should not be switched Scenario 2 - Primary and standby database should not be switched Scenario 3 - Primary and standby database should not be switched Scenario 4 - Primary and standby database should not be switched | Scenario 1 - Primary and standby database are not switched Scenario 2 - Primary and standby database are not switched Scenario 3 - Primary and standby database are not switched Scenario 4 - Primary and standby database are not switched | Pass | As expected | Pass
| 4 | Verify switching of primary and standby database with region parameter validation | SwitchingDbRegionParamValidation | In this Playbook, we tried to validate region parameter at the time of switching primary and standby database | Scenario 1 - Primary and standby database should not be switched Scenario 2 - Primary and standby database should not be switched Scenario 3 - Primary and standby database should not be switched Scenario 4 - Primary and standby database should not be switched | Scenario 1 - Primary and standby database are not switched Scenario 2 - Primary and standby database are not switched Scenario 3 - Primary and standby database are not switched Scenario 4 - Primary and standby database are not switched | Pass | As expected | Pass
Changing RDS Instance Type | 1 | Verify changing of RDS instance type with command parameter validation | ChangingInstanceTypeCommandParamValidation | In this Playbook, we tried to validate command parameter at the time of changing RDS instance type | Scenario 1 - Instance type should not be changed Scenario 2 - Instance type should not be changed Scenario 3 - Instance type should not be changed Scenario 4 - Instance type should not be changed | Scenario 1 - Instance type is not changed Scenario 2 - Instance type is not changed Scenario 3 - Instance type is not changed Scenario 4 - Instance type is not changed | Pass | As expected | Pass
| 2 | Verify changing of RDS instance type with instance class parameter validation | ChangingInstanceTypeInstanceClassParamValidation | In this Playbook, we tried to validate instance class parameter at the time of changing RDS instance type | Scenario 1 - Instance type should not be changed Scenario 2 - Instance type should not be changed Scenario 3 - Instance type should not be changed Scenario 4 - Instance type should not be changed | Scenario 1 - Instance type is not changed Scenario 2 - Instance type is not changed Scenario 3 - Instance type is not changed Scenario 4 - Instance type is not changed | Pass | As expected | Pass
| 3 | Verify changing of RDS instance type with instance id parameter validation | ChangingInstanceTypeInstanceIdParamValidation | In this Playbook, we tried to validate instance id parameter at the time of database creation | Scenario 1 - Instance type should not be changed Scenario 2 - Instance type should not be changed Scenario 3 - Instance type should not be changed Scenario 4 - Instance type should not be changed | Scenario 1 - Instance type is not changed Scenario 2 - Instance type is not changed Scenario 3 - Instance type is not changed Scenario 4 - Instance type is not changed | Pass | As expected | Pass
| 4 | Verify changing of RDS instance type with instance storage parameter validation | ChangingInstanceTypeInstanceStorageParamValidation | In this Playbook, we tried to validate instance storage parameter at the time of changing RDS instance type | Scenario 1 - Instance type should not be changed Scenario 2 - Instance type should not be changed Scenario 3 - Instance type should not be changed Scenario 4 - Instance type should not be changed | Scenario 1 - Instance type is not changed Scenario 2 - Instance type is not changed Scenario 3 - Instance type is not changed Scenario 4 - Instance type is not changed | Pass | As expected | Pass
| 5 | Verify changing of RDS instance type with pay type parameter validation | ChangingInstanceTypePayTypeParamValidation | In this Playbook, we tried to validate pay type parameter at the time of changing RDS instance type | Scenario 1 - Instance type should not be changed Scenario 2 - Instance type should not be changed Scenario 3 - Instance type should not be changed Scenario 4 - Instance type should not be changed | Scenario 1 - Instance type is not changed Scenario 2 - Instance type is not changed Scenario 3 - Instance type is not changed Scenario 4 - Instance type is not changed | Pass | As expected | Pass
| 6 | Verify changing of RDS instance type with region parameter validation | ChangingInstanceTypeRegionParamValidation | In this Playbook, we tried to validate region parameter at the time of changing RDS instance type | Scenario 1 - Instance type should not be changed Scenario 2 - Instance type should not be changed Scenario 3 - Instance type should not be changed Scenario 4 - Instance type should not be changed | Scenario 1 - Instance type is not changed Scenario 2 - Instance type is not changed Scenario 3 - Instance type is not changed Scenario 4 - Instance type is not changed | Pass | As expected | Pass
| 7 | Verify changing of RDS instance type with all parameters | ChangingInstanceTypeWithAllParams | In this Playbook, we tried changing RDS instance type with all the parameters | Instance type should be changed | Instance type is changed | Pass | As expected | Pass | API Error
| 8 | Verify changing of Postgre instance type | ChangingPostgreInstanceType | In this Playbook, we tried changing Postgre instance type | Instance type should be changed | Instance type is changed | Pass | As expected | Pass
| 9 | Verify changing of PPAS instance type | ChangingPPASInstanceType | In this Playbook, we tried changing PPAS instance type | Instance type should be changed | Instance type is changed | Pass | As expected | Pass

## Account Management
Module Name: rds_acct_mgmt.py Description: Create and Delete account, granting and revoking Account permissions
Resetting Account and Resetting Account Password
|  | Click2Cloud Testing Team Status |  | Aliyun Team Status
|  | Total Test Cases | 43 | Total Test Cases | 43
|  | No. of Test Case Passed | 43 | No. of Test Case Passed | 43
|  | No. of Test Case Failed | 0 | No. of Test Case Failed | 0
|  | No. of Test Case Partially Passed | 0 | No. of Test Case Partially Passed | 0
|  | No. of Test Case have Concern | 0 | No. of Test Case have Concern | 0
[6 empty] | Click2Cloud Testing Team |  | Aliyun Testing Team
| # | Test Case Name | Playbook File | Description | Expected Result | C2C Actual Result | C2C Status | Aliyun Actual Result | Aliyun Status | Comment for Failure
Create Account | 1 | Verify account creation with Command parameter validation | CreateAccountCommandParamValidation | In this Playbook, we tried to validate Command parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should not be created Scenario 3 - Account should not be created Scenario 4 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is not created Scenario 3 - Account is not created Scenario 4 - Account is not created | Pass | As Expected | Pass
| 2 | Verify account creation with Description parameter validation | CreateAccountDescriptionParamValidation | In this Playbook, we tried to validate Description parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should be created Scenario 2.1 - Account should be deleted Scenario 3 - Account should be created Scenario 3.1 - Account should be deleted Scenario 4 - Account should not be created Scenario 5 - Account should not be created Scenario 6 - Account should not be created Scenario 7 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is created Scenario 2.1 - Account is deleted Scenario 3 - Account is created Scenario 3.1 - Account is deleted Scenario 4 - Account is not created Scenario 5 - Account is not created Scenario 6 - Account is not created Scenario 7 - Account is not created | Pass | As Expected | Pass
| 3 | Verify account creation with Instance Id parameter validation | CreateAccountInstanceIdParamValidation | In this Playbook, we tried to validate Instance Id parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should not be created Scenario 3 - Account should not be created Scenario 4 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is not created Scenario 3 - Account is not created Scenario 4 - Account is not created | Pass | As Expected | Pass
| 4 | Verify account creation with Account Name parameter validation | CreateAccountNameParamValidation | In this Playbook, we tried to validate Account Name parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should not be created Scenario 3 - Account should not be created Scenario 4 - Account should not be created Scenario 5 - Account should not be created Scenario 6 - Account should be created Scenario 6.1 - Account should be deleted Scenario 7 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is not created Scenario 3 - Account is not created Scenario 4 - Account is not created Scenario 5 - Account is not created Scenario 6 - Account is created Scenario 6.1 - Account is deleted Scenario 7 - Account is not created | Pass | As Expected | Pass | Thread dependency on instance status
| 5 | Verify account creation with Account Password parameter validation | CreateAccountPasswordParamValidation | In this Playbook, we tried to validate Account Password parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should not be created Scenario 3 - Account should not be created Scenario 4 - Account should not be created Scenario 5 - Account should not be created Scenario 6 - Account should be created Scenario 6.1 - Account should be deleted Scenario 7 - Account should be created Scenario 7.1 - Account should be deleted Scenario 8 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is not created Scenario 3 - Account is not created Scenario 4 - Account is not created Scenario 5 - Account is not created Scenario 6 - Account is created Scenario 6.1 - Account is deleted Scenario 7 - Account is created Scenario 7.1 - Account is deleted Scenario 8 - Account is not created | Pass | As Expected | Pass
| 6 | Verify account creation with Region parameter validation | CreateAccountRegionParamValidation | In this Playbook, we tried to validate Region parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should not be created Scenario 3 - Account should not be created Scenario 4 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is not created Scenario 3 - Account is not created Scenario 4 - Account is not created | Pass | As Expected | Pass
| 7 | Verify account creation with Account Type parameter validation | CreateAccountTypeParamValidation | In this Playbook, we tried to validate Account Type parameter at the time of account creation | Scenario 1 - Account should not be created Scenario 2 - Account should be created Scenario 2.1 - Account should be deleted Scenario 3 - Account should not be created Scenario 4 - Account should not be created | Scenario 1 - Account is not created Scenario 2 - Account is created Scenario 2.1 - Account is deleted Scenario 3 - Account is not created Scenario 4 - Account is not created | Pass | As Expected | Pass
| 8 | Verify account creation with all parameters | CreateAccountWithAllParameters | In this Playbook, we tried account creation with all parameters | Scenario 1 - Account should be created Scenario 2 - Account should be deleted | Scenario 1 - Account is created Scenario 2 - Account is deleted | Pass | As Expected | Pass | Thread dependency on instance status
| 9 | Verify super account creation | CreateSuperAccount | In this Playbook, we tried super account creation | Scenario 1- Account should be created Scenario 2 - Account should not be created Scenario 3 - Account should not be deleted | Scenario 1 - Account is created Scenario 2 - Account is not created Scenario 3 - Account is not deleted | Pass | As Expected | Pass | Thread dependency on instance status
Delete Account | 1 | Verify account deletion with command parameter validation | DeleteAccountCommandParamValidation | In this Playbook, we tried to delete account with command parameter validation | Scenario 1 - Account should not be deleted Scenario 2 - Account should not be deleted Scenario 3 - Account should not be deleted Scenario 4 - Account should not be deleted | Scenario 1 - Account is not deleted Scenario 2 - Account is not deleted Scenario 3 - Account is not deleted Scenario 4 - Account is not deleted | Pass | As Expected | Pass
| 2 | Verify account deletion in Postgre instance | DeleteAccountInPostgreInstance | In this Playbook, we tried to delete account in Postgre instance | Account should not be deleted | Account is not deleted | Pass | As Expected | Pass
| 3 | Verify account deletion in PPAS instance | DeleteAccountInPPASInstance | In this Playbook, we tried to delete account in PPAS instance | Account should not be deleted | Account is not deleted | Pass | As Expected | Pass
| 4 | Verify account deletion with Instance Id parameter validation | DeleteAccountInstanceIdParamValidation | In this Playbook, we tried to delete account with Instance Id parameter validation | Scenario 1 - Account should not be deleted Scenario 2 - Account should not be deleted Scenario 3 - Account should not be deleted Scenario 4 - Account should not be deleted | Scenario 1 - Account is not deleted Scenario 2 - Account is not deleted Scenario 3 - Account is not deleted Scenario 4 - Account is not deleted | Pass | As Expected | Pass
| 5 | Verify account deletion with Account Name parameter validation | DeleteAccountNameParamValidation | In this Playbook, we tried to delete account with Account Name parameter validation | Scenario 1 - Account should not be deleted Scenario 2 - Account should not be deleted Scenario 3 - Account should not be deleted Scenario 4 - Account should not be deleted | Scenario 1 - Account is not deleted Scenario 2 - Account is not deleted Scenario 3 - Account is not deleted Scenario 4 - Account is not deleted | Pass | As Expected | Pass
| 6 | Verify account deletion with all parameter | DeleteAccountWithAllParameters | In this Playbook, we tried to delete account with all parameter | Scenario 1 - Account should be created Scenario 2 - Account should be deleted | Scenario 1 - Account is created Scenario 2 - Account is deleted | Pass | As Expected | Pass
Grant Account Permissions | 1 | Verify granting of account permission with account name parameter validation | GrantAccPermissionAccountNameParamValidation | In this Playbook, we tried to grant permissions to account with account name parameter validation | Scenario 1 - Account permission should not be granted Scenario 2 - Account permission should not be granted Scenario 3 - Account permission should not be granted Scenario 4 - Account permission should not be granted | Scenario 1 - Account permission is not granted Scenario 2 - Account permission is not granted Scenario 3 - Account permission is not granted Scenario 4 - Account permission is not granted | Pass | As Expected | Pass
| 2 | Verify granting of account permission with account priviledge parameter validation | GrantAccPermissionAccountPriviledgeParamValidation | In this Playbook, we tried to grant permissions to account with account privilrdge parameter validation | Scenario 1 - Account permission should not be granted Scenario 2 - Account permission should not be granted Scenario 3 - Account permission should not be granted Scenario 4 - Account permission should not be granted | Scenario 1 - Account permission is not granted Scenario 2 - Account permission is not granted Scenario 3 - Account permission is not granted Scenario 4 - Account permission is not granted | Pass | As Expected | Pass
| 3 | Verify granting of account permission with command parameter validation | GrantAccPermissionCommandParamValidation | In this Playbook, we tried to grant permissions to account with command parameter validation | Scenario 1 - Account permission should not be granted Scenario 2 - Account permission should not be granted Scenario 3 - Account permission should not be granted Scenario 4 - Account permission should not be granted | Scenario 1 - Account permission is not granted Scenario 2 - Account permission is not granted Scenario 3 - Account permission is not granted Scenario 4 - Account permission is not granted | Pass | As Expected | Pass
| 4 | Verify granting of account permission with database name parameter validation | GrantAccPermissionDbNameParamValidation | In this Playbook, we tried to grant permissions to account with database name parameter validation | Scenario 1 - Account permission should not be granted Scenario 2 - Account permission should not be granted Scenario 3 - Account permission should not be granted Scenario 4 - Account permission should not be granted | Scenario 1 - Account permission is not granted Scenario 2 - Account permission is not granted Scenario 3 - Account permission is not granted Scenario 4 - Account permission is not granted | Pass | As Expected | Pass
| 5 | Verify granting of account permission with instance id parameter validation | GrantAccPermissionInstanceIdParamValidation | In this Playbook, we tried to grant permissions to account with instance id parameter validation | Scenario 1 - Account permission should not be granted Scenario 2 - Account permission should not be granted Scenario 3 - Account permission should not be granted Scenario 4 - Account permission should not be granted | Scenario 1 - Account permission is not granted Scenario 2 - Account permission is not granted Scenario 3 - Account permission is not granted Scenario 4 - Account permission is not granted | Pass | As Expected | Pass
| 6 | Verify granting of account permission with all parameters | GrantAccPermissionsWithAllParams | In this Playbook, we tried to grant permissions to account with all parameters | Scenario 1 - Account should be created Scenario 2 - Database should be created Scenario 3 - Account permission should be granted Scenario 4 - Account permission should be revoked Scenario 5 - Account should be deleted Scenario 6 - Database should be deleted | Scenario 1 - Account is created Scenario 2 - Database is created Scenario 3 - Account permission is granted Scenario 4 - Account permission is revoked Scenario 5 - Account is deleted Scenario 6 - Database is deleted | Pass | As Expected | Pass
| 7 | Verify granting of account permission to instance of different region | GrantAccPermissionToDiffDbInstance | In this Playbook, we tried to grant permissions to instance of different region | Account permission should not be granted | Account permission is not granted | Pass | As Expected | Pass
Revoke Account Permissions | 1 | Verify revoking of account permission with all parameters | RevokeAccountPermissionsWithAllParams | In this Playbook, we tried to revoke permissions of account with all parameters | Scenario 1 - Account should be created Scenario 2 - Database should be created Scenario 3 - Account permission should be granted Scenario 4 - Account permission should be revoked Scenario 5 - Account should be deleted Scenario 6 - Database should be deleted | Scenario 1 - Account is created Scenario 2 - Database is created Scenario 3 - Account permission is granted Scenario 4 - Account permission is revoked Scenario 5 - Account is deleted Scenario 6 - Database is deleted | Pass | As Expected | Pass
| 2 | Verify revoking of account permission with account name parameter validation | RevokeAccPermissionAccountNameParamValidation | In this Playbook, we tried to revoke permissions of account with account name parameter validation | Scenario 1 - Account permission should not be revoke Scenario 2 - Account permission should not be revoke Scenario 3 - Account permission should not be revoke Scenario 4 - Account permission should not be revoke | Scenario 1 - Account permission is not revoke Scenario 2 - Account permission is not revoke Scenario 3 - Account permission is not revoke Scenario 4 - Account permission is not revoke | Pass | As Expected | Pass
| 3 | Verify revoking of account permission with command parameter validation | RevokeAccPermissionCommandParamValidation | In this Playbook, we tried to revoke permissions of account with command parameter validation | Scenario 1 - Account permission should not be revoke Scenario 2 - Account permission should not be revoke Scenario 3 - Account permission should not be revoke Scenario 4 - Account permission should not be revoke | Scenario 1 - Account permission is not revoke Scenario 2 - Account permission is not revoke Scenario 3 - Account permission is not revoke Scenario 4 - Account permission is not revoke | Pass | As Expected | Pass
| 4 | Verify revoking of account permission with database name parameter validation | RevokeAccPermissionDbNameParamValidation | In this Playbook, we tried to revoke permissions of account with database name parameter validation | Scenario 1 - Account permission should not be revoke Scenario 2 - Account permission should not be revoke Scenario 3 - Account permission should not be revoke Scenario 4 - Account permission should not be revoke | Scenario 1 - Account permission is not revoke Scenario 2 - Account permission is not revoke Scenario 3 - Account permission is not revoke Scenario 4 - Account permission is not revoke | Pass | As Expected | Pass
| 5 | Verify revoking of account permission with instance id parameter validation | RevokeAccPermissionInstanceIdParamValidation | In this Playbook, we tried to revoke permissions of account with instance id parameter validation | Scenario 1 - Account permission should not be revoke Scenario 2 - Account permission should not be revoke Scenario 3 - Account permission should not be revoke Scenario 4 - Account permission should not be revoke | Scenario 1 - Account permission is not revoke Scenario 2 - Account permission is not revoke Scenario 3 - Account permission is not revoke Scenario 4 - Account permission is not revoke | Pass | As Expected | Pass
| 6 | Verify revoking of account permission without any permissions | RevokeAccPermissionsForAccWithoutPermissions | In this Playbook, we tried to revoke permissions of account without any permissions | Scenario 1 - Account should be created Scenario 2 - Database should be created Scenario 3 - Account permission should not be revoked Scenario 4 - Account should be deleted Scenario 5 - Database should be deleted | Scenario 1 - Account is created Scenario 2 - Database is created Scenario 3 - Account permission is not revoked Scenario 4 - Account is deleted Scenario 5 - Database is deleted | Pass | As Expected | Pass
Resetting Account | 1 | Verify resetting of account with command parameter validation | ResettingAccountCommandParamValidation | In this Playbook, we tried to reset account with command parameter validation | Scenario 1 - Account should not be reset Scenario 2 - Account should not be reset Scenario 3 - Account should not be reset | Scenario 1 - Account is not reset Scenario 2 - Account is not reset Scenario 3 - Account is not reset | Pass | As Expected | Pass
| 2 | Verify resetting of account with instance id parameter validation | ResettingAccountDbInstanceIdParamValidation | In this Playbook, we tried to reset account with instance id parameter validation | Scenario 1 - Account should not be reset Scenario 2 - Account should not be reset Scenario 3 - Account should not be reset Scenario 4 - Account should not be reset | Scenario 1 - Account is not reset Scenario 2 - Account is not reset Scenario 3 - Account is not reset Scenario 4 - Account is not reset | Pass | As Expected | Pass
| 3 | Verify resetting account of MySQL instance | ResettingAccountOfMySQLInstance | In this Playbook, we tried to reset account of MySQL instance | Scenario 1 - Account should be created Scenario 2 - Account should not be reset Scenario 3 - Account should be deleted | Scenario 1 - Account is created Scenario 2 - Account is not reset Scenario 3 - Account is deleted | Pass | As Expected | Pass
| 4 | Verify resetting account of Postgre instance | ResettingAccountOfPostgreInstance | In this Playbook, we tried to reset account of Postgre instance | Scenario 1 - Account should be created Scenario 2 - Account should be reset | Scenario 1 - Account is created Scenario 2 - Account is reset | Pass | As Expected | Pass | Thread dependency on instance status
| 5 | Verify resetting account of PPAS instance | ResettingAccountOfPPASInstance | In this Playbook, we tried to reset account of PPAS instance | Scenario 1 - Account should be created Scenario 2 - Account should be reset | Scenario 1 - Account is created Scenario 2 - Account is reset | Pass | As Expected | Pass | Thread dependency on instance status
| 6 | Verify resetting of account with Account Name parameter validation | ResettingAccountWithAccountNameParamValidation | In this Playbook, we tried to reset account with with Account Name parameter validation | Scenario 1 - Account should not be reset Scenario 2 - Account should not be reset Scenario 3 - Account should not be reset Scenario 4 - Account should not be reset | Scenario 1 - Account is not reset Scenario 2 - Account is not reset Scenario 3 - Account is not reset Scenario 4 - Account is not reset | Pass | As Expected | Pass
| 7 | Verify resetting of account with Account Password parameter validation | ResettingAccountWithAccPasswordParamValidation | In this Playbook, we tried to reset account with Account Password parameter validation | Scenario 1 - Account should not be reset Scenario 2 - Account should not be reset Scenario 3 - Account should not be reset Scenario 4 - Account should not be reset | Scenario 1 - Account is not reset Scenario 2 - Account is not reset Scenario 3 - Account is not reset Scenario 4 - Account is not reset | Pass | As Expected | Pass
Resetting Account Password | 1 | Verify resetting of account password with Account Name parameter validation | ResettingInstancePasswordAccountNameParamValidation | In this Playbook, we tried to reset account password with with Account Name parameter validation | Scenario 1 - Account password should not be reset Scenario 2 - Account password should not be reset Scenario 3 - Account password should not be reset Scenario 4 - Account password should not be reset | Scenario 1 - Account password is not reset Scenario 2 - Account password is not reset Scenario 3 - Account password is not reset Scenario 4 - Account password is not reset | Pass | As Expected | Pass
| 2 | Verify resetting of account Password with Account Password parameter validation | ResettingInstancePasswordAccPasswordParamValidation | In this Playbook, we tried to reset account Password with Account Password parameter validation | Scenario 1 - Account password should not be reset Scenario 2 - Account password should not be reset Scenario 3 - Account password should not be reset Scenario 4 - Account password should not be reset | Scenario 1 - Account password is not reset Scenario 2 - Account password is not reset Scenario 3 - Account password is not reset Scenario 4 - Account password is not reset | Pass | As Expected | Pass
| 3 | Verify resetting of account password with command parameter validation | ResettingInstancePasswordCommandParamValidation | In this Playbook, we tried to reset account password with command parameter validation | Scenario 1 - Account password should not be reset Scenario 2 - Account password should not be reset Scenario 3 - Account password should not be reset | Scenario 1 - Account password is not reset Scenario 2 - Account password is not reset Scenario 3 - Account password is not reset | Pass | As Expected | Pass
| 4 | Verify resetting of account password with instance id parameter validation | ResettingInstancePasswordDbInstanceIdParamValidation | In this Playbook, we tried to reset account password with instance id parameter validation | Scenario 1 - Account password should not be reset Scenario 2 - Account password should not be reset Scenario 3 - Account password should not be reset Scenario 4 - Account password should not be reset | Scenario 1 - Account password is not reset Scenario 2 - Account password is not reset Scenario 3 - Account password is not reset Scenario 4 - Account password is not reset | Pass | As Expected | Pass
| 5 | Verify resetting account password of Postgre instance | ResettingInstancePasswordOfPostgreInstance | In this Playbook, we tried to reset passwordaccount of Postgre instance | Scenario 1 - Account should be created Scenario 2 - Account paaaword should be reset | Scenario 1 - Account is created Scenario 2 - Account password is reset | Pass | As Expected | Pass
| 6 | Verify resetting account password of PPAS instance | ResettingInstancePasswordOfPPASInstance | In this Playbook, we tried to reset account password of PPAS instance | Scenario 1 - Account should be created Scenario 2 - Account password should be reset | Scenario 1 - Account is created Scenario 2 - Account password is reset | Pass | As Expected | Pass
| 7 | Verify resetting account password same as the old one | ResettingInstancePasswordSameAsOldOne | In this Playbook, we tried to reset account password same as the old one | Scenario 1 - Account should be created Scenario 2 - Account password should be reset Scenario 3 - Account should be deleted | Scenario 1 - Account is created Scenario 2 - Account password is reset Scenario 3 - Account is deleted | Pass | As Expected | Pass
| 8 | Verify resetting of account password with all parameters | ResettingInstancePasswordWithAllParameters | In this Playbook, we tried to reset account password with all parameters | Scenario 1 - Account should be created Scenario 2 - Account password should be reset Scenario 3 - Account should be deleted | Scenario 1 - Account is created Scenario 2 - Account password is reset Scenario 3 - Account is deleted | Pass | As Expected | Pass | Thread dependency on instance status