## Estimation
Cloud Analysis
Name | Cloud Name | API / Interfaces | SDK | DevOps Tools Implementation | Column1 | Days required (25/07/18) | Days(4 Resources)(01/08/18) | Status
|  |  |  | Completed | Not Completed
Ashish M. | AWS | Completed | Completed | 4 | 12 | 2 | 2 | Completed
Ashwini | Huawei | Completed | Completed | 4 | 12 | 2 | 2 | Completed
Rohini | Ucloud | Completed | Ashish R. Completed | 0 | 16 | 4 | 3 | Completed
Ashish M. | Azure | Completed | Completed | 4 | 12 | 2 | 2 | Completed
Rohini | Tencent | Completed | Ashish R. Completed | 0 | 16 | 4 | 3 | IN-Progress
Suchita | Baidu | Completed | Completed | 4 | 12 | 2 | 2 | Completed
Ashwini | Alibaba | Completed | Completed | 4 | 12 | 2 | 2 | Completed
Suchita | JD Cloud | Completed | Ashish R. Completed | 0 | 16 | 3 | 2 | IN-Progress
Rohini | Qing | Completed | Ashish R. Completed | 0 | 16 | 4 | 2 | Completed
Ashwini | Oracle | Completed | Completed | 0 | 16 | 3 | 3 | Completed
Ashwini | Openshift | Completed | Ashwini , Ashish Started (Not found) | 0 | 16 | 4 | 2 | Completed
Ashwini | Cloudstack | Completed | Ashwini, Ashish Started (Not found) | 0 | 16 | 4 | 2 | IN-Progress
Ashwini | Rackspace | Completed | Completed | 0 | 16 | 3 | 2 | Completed
Not Started | IBM | Completed | Ashish R. Started | 0 | 16 | 4 | 2 | Not Started
Suchita | Google | Completed | Completed | 0 | 16 | 4 | 4 | Completed
All three | Openstack | Completed | Completed | 0 | Complete | 4 | 0 | Completed (Inserted in Sharepoint list)
Not Started | Intel | Ashish R. Started | No Started Yet | 0 | 16 | 6 | 5 | Not Started
[6 empty] | Total Days - 57 | Total Days - 40