## Cloud Brain Plan
Cloud Brain Development Plan:
|  | Start Date | 2018-08-20
|  | End Date | 2019-01-14
|  | Total Days | 106
|  | No of Resources | 5
Task | Duration (In Days) | Start Date | End Date | Resource | Status
Analysis Phase
ManageIq features and Database analysis for Cloud Brain (Cloud Intel ,Topology, Optimize) | 10 | 2018-08-20 | 2018-08-31 | Dev-1,Dev-2,Dev-3,Dev-4 | Done
Analysis of Azure and AWS SDK/API (CPU, Memory utilization, Number of Instances etc) to get data for Reports | 4 | 2018-09-03 | 2018-09-06 | Dev-3, Dev-1 | Done
Analysis of Cloud Intel Reports | 3 | 2018-09-04 | 2018-09-06 | Dev-4 | Done
First Phase
Landing, Login and Registration Page
Design and Development of Landing Page | 1 | 2018-09-07 | 2018-09-07 | Dev - 1 | Ongoing
Design and Development of Login Page | 1 | 2018-09-07 | 2018-09-07 | Dev - 3 | Ongoing
Design and Development of Registration Page | 1 | 2018-09-07 | 2018-09-07 | Dev - 4 | Ongoing
Design and Development of SideMenuBar | 1 | 2018-09-07 | 2018-09-07 | Dev - 2 | Ongoing
Integration testing and bug fixing | 1 | 2018-09-10 | 2018-09-10 | Dev - 3, Dev-4 and Testing Resource
Integration of Gap-Analysis (Comparision) Report with Cloud Brain
Integration of Gap-Analysis (Comparision) Report with Cloud Brain | 1 | 2018-09-10 | 2018-09-10 | Dev - 1, Dev-2 | Not Started
Integration testing and bug fixing | 1 | 2018-09-11 | 2018-09-11 | Dev - 1, Dev-2 , Dev-3, Dev-4 and Testing Resource | Not Started
Sprint Release (First)
Deployment of First Sprint release with Login,Registration,Landing page and Gap-Analysis Report | 1 | 2018-09-12 | 2018-09-12 | Networking Resource and Dev Resources | Not Started
Integration of Cloud Monitoring with Cloud Brain
Integration of Cloud Monitoring with Cloud Brain (UI ONLY) | 10 | 2018-09-13 | 2018-09-26 | Dev - 1, Dev - 2 | Not Started
Development of Monitoring Dashboard | 3 | 2018-09-27 | 2018-10-01 | Dev - 1, Dev - 2 | Not Started
Integration testing and bug fixing | 3 | 2018-10-02 | 2018-10-04 | Dev - 1, Dev - 2 and Testing Resource | Not Started
Integration of Cloud Compare with Cloud Brain (Cost Calculator, Services & Reporting)
Stabilizing Cost Calculator (Compute, Storage ,Networking) | 10 | 2018-09-13 | 2018-09-26 | Dev - 3 and Dev - 4 | Not Started
Development of Compare Dashboard (Power BI Reporting) | 4 | 2018-09-27 | 2018-10-02 | Dev - 3 and Dev - 4 | Not Started
Integration testing and bug fixing | 4 | 2018-10-03 | 2018-10-08 | Dev - 3, Dev - 4 and Testing Resource | Not Started
Development of Provider
Design and development of Manage Cloud Accounts | 1 | 2018-10-05 | 2018-10-05 | Dev - 1, Dev - 2 | Not Started
Integration testing and bug fixing | 1 | 2018-10-08 | 2018-10-08 | Dev - 1, Dev - 2 and Testing Resource | Not Started
Sprint Release (Second)
Deployment of Second Sprint release with Compare and Monitoring and Provider functionality | 1 | 2018-10-09 | 2018-10-09 | Networking Resource and Dev Resources | Not Started
Development Of Cloud Intel
Reports
Development Of Recently discovered VM | 3 | 2018-10-10 | 2018-10-12 | Dev - 1 | Not Started
Development Of Vendor OS | 3 | 2018-10-10 | 2018-10-12 | Dev - 2 | Not Started
Development Of VM Disk Usage | 3 | 2018-10-10 | 2018-10-12 | Dev - 3 | Not Started
Development Of VM Location and Size | 3 | 2018-10-10 | 2018-10-12 | Dev - 4 | Not Started
Testing of Reports | 3 | 2018-10-15 | 2018-10-17 | Testing Resorce | Not Started
Development Of Top CPU Consumers | 3 | 2018-10-15 | 2018-10-17 | Dev - 1 | Not Started
Development Of Top Memory Consumers | 3 | 2018-10-15 | 2018-10-17 | Dev - 2 | Not Started
Development Of Top Storage Consumers | 3 | 2018-10-15 | 2018-10-17 | Dev - 3 | Not Started
Development of VMs with Avg Daily Mem < 50% | 3 | 2018-10-15 | 2018-10-17 | Dev - 4 | Not Started
Testing of Reports | 3 | 2018-10-18 | 2018-10-22 | Testing Resorce | Not Started
Development of VMs with Avg Daily Mem > 95% | 3 | 2018-10-18 | 2018-10-22 | Dev - 1 | Not Started
Development of VMs with Avg Daily CPU > 85% | 3 | 2018-10-18 | 2018-10-22 | Dev - 2 | Not Started
Development of VMs with Avg Daily Mem > 80% | 3 | 2018-10-18 | 2018-10-22 | Dev - 3 | Not Started
Integration testing and bug fixing | 5 | 2018-10-23 | 2018-10-29 | Dev - 1, Dev - 2, Dev - 3, Dev - 4 and Testing Resource | Not Started
Dashboard
Design and development of Dashboard | 5 | 2018-10-30 | 2018-11-05 | Dev - 1 & Dev - 2 | Not Started
Integration testing and bug fixing | 3 | 2018-11-06 | 2018-11-08 | Dev - 1, Dev - 2 and Testing Resource | Not Started
Development Of Billing
Design and development of Billing | 5 | 2018-10-30 | 2018-11-05 | Dev - 3 & Dev - 4 | Not Started
Integration testing and bug fixing | 3 | 2018-11-06 | 2018-11-08 | Dev - 3, Dev - 4 and Testing Resource | Not Started
Sprint Release (Fourth)
Deployment of Fourth Sprint release with Billing functionality | 1 | 2018-11-09 | 2018-11-09 | Networking Resource and Dev Resources | Not Started
Second Phase
Development Of Topology
Design and development of Topology | 8 | 2018-11-12 | 2018-11-21 | Dev - 1 & Dev - 2 | Not Started
Integration testing and bug fixing | 4 | 2018-11-22 | 2018-11-27 | Dev - 1, Dev - 2 and Testing Resource | Not Started
Development Of Optimize
Utilization
Design and development of Utilization | 8 | 2018-11-12 | 2018-11-21 | Dev - 3 & Dev - 4 | Not Started
Integration testing and bug fixing | 4 | 2018-11-22 | 2018-11-27 | Dev - 3, Dev - 4 and Testing Resource | Not Started
Planning
Design and development of Planning | 8 | 2018-11-12 | 2018-11-21 | Dev - 1 & Dev - 2 | Not Started
Integration testing and bug fixing | 4 | 2018-11-22 | 2018-11-27 | Dev - 1, Dev - 2 and Testing Resource | Not Started
Bottleneck
Design and development of Bottleneck | 8 | 2018-11-28 | 2018-12-07 | Dev - 3 & Dev - 4 | Not Started
Integration testing and bug fixing | 4 | 2018-12-10 | 2018-12-13 | Dev - 3, Dev - 4 and Testing Resource | Not Started
Sprint Release (Fifth)
Deployment of Fifth Sprint release with Optimize and Topology functionality | 1 | 2018-12-14 | 2018-12-14 | Networking Resource and Dev Resources | Not Started
Final Testing and Bug Fixing
Integration testing and bug fixing | 10 | 2018-12-17 | 2018-12-28 | Dev - 1, Dev - 2, Dev - 3, Dev - 4 and Testing Resource | Not Started
Buffer
Buffer for unknown complexity and research ( 8% - 9% of total Days) | 10 | 2018-12-31 | 2019-01-11 | Dev - 1, Dev - 2, Dev - 3, Dev - 4 and Testing Resource | Not Started
Sprint Release (Final)
Deployment of Final Sprint release with all functionalities | 1 | 2019-01-14 | 2019-01-14 | Networking Resource and Dev Resources | Not Started
Third Phase
Integration Of Migration with Cloud Brain
Integration Of Migration with Cloud Brain
Formulas:
End Date = WORKDAY([Start Date],[Duration (In Days)]-1)
Start Date = WORKDAY([Start Date, row above],0)
Start Date = WORKDAY([End Date, row above],1)