## Assumptions
Assumption(s)
* The estimate includes effort required for developing and testing Telefonica Cloud * We assume that, the APIs is already available with documentation. * Estimate may vary if new feature is added. * We assume that, the Huawei team will help in converting English language keys and content to other supporting languages * All documentations and user guide will be created in English language only. * We assume that, the Ruby SDK will be available before the development of ManageIQ provider * We assume that, all Ruby SDK interfaces which we need in ManageIQ will work for Telefonica Cloud

## Estimation
***High level estimate
Development & Testing
Project Tasks / Features and Activities | Analysis | ManageIQ Testing, Bug fixing and stabilization (hrs.) | Implementation and Unit Test (hrs.) | User Guide and help document (hrs.)
(hrs.)
Requirement Gathering | 40 | - | - | -
Requirement Gathering and analyzing requirement
Environment Readiness
Development Environment Setup | 32 | - | - | -
Staging Environment Setup
Repository Setup
Execution
Analyzing/Developing Dependencies | 24 | - | 20 | -
Developing required dependencies in manageiq-smartstate repository [https://github.com/ManageIQ/manageiq-smartstate]
Telefonica ManageIQ Providers
Common
Modifying existing OpenStack Lib folder to make it compatible with Telefonica | - | 64 | 120 | -
Modifying the Inventories and Inventories collections as per ManageIQ Database
Modify the refresh parser as per Telefonica parameters
Unit Test Script
Modification in OpenStack Cloud Manager | - | 64 | 120 | -
Event Collection and Catcher
Metric Collection and Handling
Implementation of Rollups mechanism
Provisioning
Orchestration
Lifecycle Management
SmartState Analysis
Refresh Workers
Unit Test Script
Modification in OpenStack Network Manager | - | 64 | 64 | -
Event Collection and Catcher
Metric Collection and Handling
Implementation of Rollups mechanism
Provisioning
Orchestration
Lifecycle Management
SmartState Analysis
Refresh Workers
Unit Test Script
Modification in OpenStack Storage Manager | - | 64 | 64 | -
Event Collection and Catcher
Metric Collection and Handling
Implementation of Rollups mechanism
Provisioning
Orchestration
Lifecycle Management
SmartState Analysis
Refresh Workers
Unit Test Script
Other | - | 64 | 120 | -
Integration of Telefonica Provider in ManageIQ Repository
Integration of Telefonica Provider in ManageIQ UI Repository
Modifying the locale language packs
Unit Test Script
Help Document |  |  |  | 56
UAT Support and feedback implementation | - | 64 | 64 | -
Individual Efforts | 96 | 384 | 572 | 56
Buffer (10%) | 10 | 38 | 57 | 6
Grand Total for Development (Hrs.) | 1219
Note on B20: Author: This will need to modify the lib folder to build the delegate compatible with Telefonica and Handle the events
Note on B25: Author: OpenStack has built both the Cloud Manager and Infra Manager