## Summary
SRN | Task | Hours | Comments | Assumptions
1 | RubySDK Development Telefonica(SDK gem with 8 interfaces) | 144 | Details | Details
Total Hours |  | 144

## Telefonica_RubySDK_Estimate
***High level estimate
| Click here for Total Hours ---> | Go to Top --->
Development & Testing
Project Tasks / Features and Activities | Analysis & Tech Documentation | Integration Testing, Bug fixing and Stabilization (hrs) | Implementation and Unit Test (hrs)
Requirement Gathering (Ruby SDK ManageIQ) |  |  |  | NOTES: * Implementation covers effort required for development of functions which will be called in ManageIQ plugin and unit tests
Requirement Gathering | 8 | 0 | 0
Analysis on requirement | 32
Technical Documentation | 0
Environment Readiness | 8
Ruby Language API Interfaces
Identity and Access Management | 0 | 4 | 8
Show project details
Elastic Volume Service | 0 | 12 | 24
List volumes details
List Availability Zones
Querying task status
Elastic Cloud Server | 0 | 16 | 32
Show Floating IP
Starting server
Restating server
Stopping ECSs in Batches
UAT Support and feedback implementation | 0
Individual Efforts | 48 | 32 | 64
Grand Total for Development (Hrs) | 144

## Assumptions
Assumption(s)
* The estimate includes effort required for developing and testing Ruby SDK for Telefonica Cloud, to be used in ManageIQ. * We assume that, the Telefonica APIs are already available with documentation. * We are considering the Native APIs for Ruby SDK. * Estimate may vary if new feature is added or if in case of Native API does not work for Telefonica Cloud. * We assume that, all Native APIs which are required for ManageIQ works for the Telefonica Cloud. * We assume that, the Huawei team will help in converting English language keys and content to other supporting languages. * All documentations and user guide if needed will be created in English language only.